## Summary
LAST LIGHT — AI ART PRODUCTION PLAN | PM revision: mobile-readable minimum; art must not delay G1–G3
Production rule | G1–G3 use primitive placeholders. P0 art is integrated only after the end-to-end run is stable (G3).
Priority | Prompt briefs | Asset packages | Visual pieces | Art est. (min) | Integration est. (min) | Release rule
P0 — Mobile minimum | 8 | 8 | 19 | 210 | 155 | Integrate post-G3; ship before any P1
P1 — Readability & feedback | 5 | 8 | 14 | 180 | 135 | Begin only after P0 is integrated and readable
P2 — Polish | 2 | 2 | 10 | 90 | 50 | Cut immediately when schedule slips
Gate | Playable requirement | Allowed art state | Exit condition
G1 — Core movement | Player can move through a portrait lane | Primitive player, walls, and collision shapes only | Movement and camera stable on device
G2 — Core loop | Hazards and altar choice function | Unity primitives; text labels permitted | Hazard timing, choice collision, and state changes work
G3 — End-to-end | Start → stages → choice → ending completes | All placeholders acceptable | Full run completes on target phone without art dependency
Post-G3 — P0 integration | Replace only mobile-critical placeholders | Traveller, relic, two hazards, altars, icons, micro-kit, HUD | P0 integrated with no readability or schedule regression
Art-director cut rules | Shadow hazard is P1. Corridor is a 6-tile micro-kit. Player animation begins static, then 2-frame move + 1 hurt frame in P1. Every asset has an implementation estimate and fallback.

## Prompt Plan
Prompt ID | Category | Priority | Stage | Gate | Prompt brief | Output | Tool | Attempts | Prompt est. (min) | Fallback | Status
P00 | Direction & Calibration | Control | Calibration | Parallel; 20 min cap | Silhouette and cluster-language calibration only | 6 traveller silhouettes; 3 hazard shapes; 2 altar pairs | ChatGPT Images | 2 | 20 | Use the art-direction document's existing silhouettes | Not Started
P01 | Character Base | P0 | Stage A - Static | Post-G3 | Compact faceless traveller base sprite | 1 static 24x24 sprite | PixelLab + Aseprite | 2 | 25 | Bone rectangle/capsule placeholder | Not Started
P02 | Relic & Lighting | P0 | Stage A - Static | Post-G3 | Sacred relic core with one scalable glow layer | 2 sprites: core + inner glow | PixelLab + Aseprite | 2 | 20 | Gold square child with scaled duplicate | Not Started
P03 | Hazards - Spikes | P0 | Stage A - Static | Post-G3 | Single repeatable spike-wall module | 1 modular sprite | PixelLab + Aseprite | 2 | 15 | Unity triangle strip | Not Started
P04 | Hazards - Blade | P0 | Stage A - Static | Post-G3 | Single cross/bar blade sprite; rotation handled in Unity | 1 sprite | PixelLab + Aseprite | 2 | 20 | Cross made from two rectangles | Not Started
P05 | Hazards - Shadow | P1 | Stage B - Feedback | After P0 | Warning line and vertical strike pair | 2 sprites | PixelLab + Aseprite | 3 | 30 | Unity line + filled rectangle | Not Started
P06 | Choice - Altars | P0 | Stage A - Static | Post-G3 | Matched safety and cost altar base pair | 2 sprites | PixelLab + Aseprite | 2 | 30 | Cyan and gold rectangles with icons | Not Started
P07 | UI - Cost Icons | P0 | Stage A - Static | Post-G3 | Coherent five-icon cost set | 5 icons | PixelLab + Aseprite | 3 | 45 | Uppercase labels plus geometric symbols | Not Started
P08 | Environment | P0 | Stage A - Micro-kit | Post-G3 | Reduced ancient corridor micro-kit | 6 tiles | PixelLab + Aseprite | 3 | 45 | Solid navy floor and stone side rails | Not Started
P09 | HUD | P0 | Stage A - Unity-native | Post-G3 | Minimal mobile HUD skin built around Unity UI shapes | 1 HUD set | Unity UI + Aseprite | 1 | 20 | Plain Unity bars and readable sans text | Not Started
P10 | Character Degradation | P1 | Stage B - Feedback | After P0 | Modular permanent-cost overlays | 3 overlays: crack, chain, sensory loss | PixelLab + Aseprite | 3 | 35 | Tint, scale, and vignette changes only | Not Started
P11 | Endings | P1 | Stage B - Outcome | After P0 | Silhouette-led ending references | 2 ending silhouettes | ChatGPT Images + Aseprite | 2 | 40 | Reuse gameplay silhouette with different light state | Not Started
P12 | VFX | P1 | Stage B - Feedback | After P0 | Procedural square-particle patterns for selection and damage | 2 Unity presets; no unique drawings required | Unity Particle System | 1 | 20 | Flash, tint, and 1-2 px knockback | Not Started
P13 | Animation Stage 2 | P1 | Stage B - Essential motion | After P0 | Add minimum readable motion after static assets work | 2 move frames + 1 hurt frame | PixelLab + Aseprite | 3 | 45 | Static sprite with bob, flash, and knockback | Not Started
P14 | Environment Polish | P2 | Stage C - Polish | After P1 | Extra decay props and global tint study | 4 props + 1 tint study | ChatGPT Images + Aseprite | 2 | 30 | Reuse micro-kit and a global overlay tint | Not Started
P15 | Animation Stage 3 | P2 | Stage C - Polish | After P1 | Upgrade motion only if the full build is stable | 2 additional move frames + idle flicker + 2 delivery poses | Aseprite | 2 | 60 | Keep Stage 2 animation | Not Started

## Asset Register
Asset ID | Category | Priority | Stage | Gate | Asset package | Pieces | Size | Prompt | Dependency | Art est. (min) | Implementation est. (min) | Fallback | Acceptance | Status
ART-01 | Character | P0 | Stage A - Static | Post-G3 | Traveller base sprite | 1 | 24 x 24 | P01 | Player footprint locked | 15 | 10 | Bone rectangle/capsule placeholder | Readable silhouette at 25% zoom and on a 6-inch phone | Not Started
ART-02 | Relic | P0 | Stage A - Static | Post-G3 | Relic core and inner glow | 2 | 8-16 px | P02 | Player pivot locked | 20 | 20 | Gold square plus scaled child | Gold remains exclusive; depletion readable by scale/alpha | Not Started
ART-03 | Hazards | P0 | Stage A - Static | Post-G3 | Spike module | 1 | 16 x 16 | P03 | Obstacle dimensions locked | 15 | 10 | Unity triangle strip | Danger silhouette is readable and repeatable without seams | Not Started
ART-04 | Hazards | P0 | Stage A - Static | Post-G3 | Moving blade base sprite | 1 | 32 x 32 | P04 | Movement path stable | 20 | 15 | Cross built from two rectangles | Fixed rotation center and clear empty-lane telegraph | Not Started
ART-05 | Choice | P0 | Stage A - Static | Post-G3 | Safety and cost altar base pair | 2 | 32 x 48 | P06 | Collision zones locked | 30 | 20 | Cyan and gold rectangles with icons | Both choices are understood within six seconds | Not Started
ART-06 | UI | P0 | Stage A - Static | Post-G3 | Five cost icons | 5 | 24 x 24 | P07 | Cost catalogue locked | 45 | 25 | Text labels plus simple geometric symbols | Readable at 32-40 px display; shape does not rely on color alone | Not Started
ART-07 | Environment | P0 | Stage A - Micro-kit | Post-G3 | Corridor micro-kit | 6 | 16 x 16 | P08 | Camera scale locked | 45 | 30 | Solid floor and wall rails | No seams, no misleading spike/cross shapes, readable lanes | Not Started
ART-08 | UI | P0 | Stage A - Unity-native | Post-G3 | HUD skin and bars | 1 set | Reference UI | P09 | UI wireframe locked | 20 | 25 | Plain Unity bars and sans-serif text | Safe-area compliant and readable at 360 x 640 | Not Started
ART-09 | Hazards | P1 | Stage B - Feedback | After P0 | Shadow warning and strike | 2 | 16 x 32 | P05 | Telegraph timing stable | 30 | 20 | Unity line plus filled rectangle | Warning and strike are visually distinct | Not Started
ART-10 | Animation | P1 | Stage B - Essential motion | After P0 | Traveller movement - Stage 2 | 2 | 24 x 24 | P13 | ART-01 integrated | 30 | 15 | Static sprite with positional bob | Shared bounds and pivot; readable at 8 fps | Not Started
ART-11 | Animation | P1 | Stage B - Essential motion | After P0 | Traveller hurt - Stage 2 | 1 | 24 x 24 | P13 | ART-01 integrated | 15 | 10 | White flash, red frame, and knockback | Damage reads in 0.15-0.25 seconds | Not Started
ART-12 | Character | P1 | Stage B - Feedback | After P0 | Permanent-cost overlays | 3 | 24 x 24 | P10 | ART-01 integrated | 35 | 25 | Tint, scale, and vignette changes | Each implemented cost creates a visible permanent change | Not Started
ART-13 | VFX | P1 | Stage B - Feedback | After P0 | Selection and damage VFX presets | 2 | 8-16 particles | P12 | Event timings locked | 10 | 30 | Flash, tint, and knockback only | Bounded effects add information and remain mobile-safe | Not Started
ART-14 | Endings | P1 | Stage B - Outcome | After P0 | Ending silhouettes | 2 | 180 x 120 minimum | P11 | Outcomes locked | 40 | 15 | Reuse gameplay silhouette with alternate light state | Outcome is readable without text | Not Started
ART-15 | Hazards | P1 | Stage B - Variety | After P0 | Spike variant | 1 | 16 x 16 | P03 | ART-03 integrated | 10 | 5 | Reuse base spike module | Adds variety without changing collision readability | Not Started
ART-16 | Relic | P1 | Stage B - Feedback | After P0 | Outer glow and flicker layer | 1 | 12-20 px | P02 | ART-02 integrated | 10 | 15 | Scale and pulse the inner glow | Low-light state remains readable without bloom | Not Started
ART-17 | Environment | P2 | Stage C - Polish | After P1 | Extra props and tint study | 5 | 8-16 px | P14 | ART-07 integrated | 30 | 20 | Reuse micro-kit with global tint | Cuttable without gameplay or choice clarity loss | Not Started
ART-18 | Animation | P2 | Stage C - Polish | After P1 | Animation upgrade - Stage 3 | 5 | 24 x 24 | P15 | ART-10 and ART-11 stable | 60 | 30 | Keep Stage 2 animation | No subpixel jitter; same bounds and pivot across frames | Not Started