## Dashboard
LAST LIGHT — Architecture & 48-Hour Production Control
Senior game-development planning sheet derived from DECISIONS.md, ROADMAP.md, TASKS.md and the production-plan PDF.
Control | Value |  | Tasks Done |  | Completion | Planned Hours |  | Remaining Hours
Elapsed jam hours | 0 |  | 0 / 24 |  | 0% | 45.5 |  | 45.5
Current gate | G1
Feature freeze | Not active
Build target | Android (pending jam-rule confirmation)
Product Snapshot | Value | Source |  | Task Status | Count | Epic | Planned h | Done h
Engine / structure | Unity 2D, portrait auto-runner | TASKS / PDF |  | Backlog | 23 | E1 Core Controller | 3 | 0
Control | One-finger horizontal drag | Locked |  | Ready | 1 | E2 Survival Loop | 3.5 | 0
Run | Six fixed stages, 3–5 minutes | Locked |  | In Progress | 0 | E3 Obstacle Framework | 4 | 0
Resources | Health and relic light are separate | Locked |  | Review/Test | 0 | E4 Level Flow | 6 | 0
Choice | Two physical offers at stage end | LL-010 |  | Done | 0 | E5 Choice & Cost | 5.5 | 0
Task estimate | 45.5 | TASKS total |  |  |  | E6 Relic & Endings | 3 | 0
Nominal buffer | 2.5 | Derived |  |  |  | E7 UX/UI | 4 | 0
[6 empty] | E8 Art/Audio Polish | 5.5 | 0
[6 empty] | E9 QA & Submission | 11 | 0
Gate | Name | Target h | Progress | Status | PM Rule | Senior-dev callout The 24 tasks total 45.5 estimated hours, leaving only 2.5 nominal hours inside a 48-hour event. G1 alone totals 10.5 hours against an 8-hour gate, so the proposed plan assumes parallel work between the developer and Claude Code. Protect integration time; cut Should work before compressing QA.
G1 | Core playable | 8 | 0% | Not Started | Proceed only when restart is stable.
G2 | Theme playable | 16 | 0% | Not Started | Vertical slice must validate the theme.
G3 | End-to-end | 28 | 0% | Not Started | Cut optional systems if this gate slips.
G4 | Mobile usable | 32 | 0% | Not Started | Blocking mobile gate.
G5 | Content complete | 38 | 0% | Not Started | Start feature freeze after this gate.
G6 | Submission ready | 48 | 0% | Not Started | Ship stable over ambitious.

## Architecture
Technical Architecture — Minimal, Data-Driven Unity 2D
Architecture is intentionally small for a 48-hour build: one gameplay scene, prefabs for stage chunks, ScriptableObjects for static content, and a run-scoped state object for mutable data. Proposed items are marked for confirmation.
1. Input InputReader |  |  | 2. Player Motor + Health |  |  | 3. Stage Flow StageDirector |  |  | 4. Choice ChoiceGate |  |  | 5. Cost / State CostApplier + RunState |  |  | 6. Outcome EndingResolver
UI presenters subscribe to C# events. ScriptableObjects hold immutable configuration. RunState owns health, light, stage index and applied modifiers. Restart rebuilds RunState and calls reset hooks; never mutate ScriptableObject assets at runtime.
Layer | Component / Script | Unity Type | Responsibility | Owns / Reads Data | Public Contract | Depends On | Reset / Lifecycle | MVP Rule |  | Architecture Decision | Choice | Why | Status | Owner | Review Gate | Failure Mode | Fallback
Composition | GameBootstrap | MonoBehaviour | Wires scene references and starts a new run. | BuildConfig, StageCatalog | StartRun(), RestartRun() | RunController, StageDirector, UI | Exists once in gameplay scene | No DI framework or service locator. |  | Scene strategy | One gameplay scene; six stage prefabs activated sequentially | Fast iteration and reliable restart | Proposed | Developer | G1 | Scene-load race / soft lock | Use additive scenes only if prefab approach fails
Run | RunController | MonoBehaviour | Authoritative run state machine: Start → Playing → Choosing → Ending → Restarting. | RunState | BeginStage(), CompleteStage(), EndRun(), Restart() | StageDirector, ChoiceGate, EndingResolver | Creates fresh RunState on restart | Only class allowed to change run phase. |  | Static vs runtime data | ScriptableObjects are immutable config; RunState is mutable | Prevents state leaking across restarts | Proposed | Developer | G2 | Asset values persist in editor | Recreate runtime copies on BeginRun
Run | RunState | Plain serializable class | Mutable run-scoped data container. | Health, light, stage index, modifier stack, chosen costs | Read-only properties + narrow mutation methods | PlayerHealth, RelicLight, CostApplier | New instance each run | Never store runtime values in ScriptableObjects. |  | Communication | Direct references for commands; C# events for presentation | Explicit dependencies without framework overhead | Proposed | Developer | G1 | Event leaks after restart | Bind/unbind in OnEnable/OnDisable
Input | InputReader | MonoBehaviour | Normalizes touch and mouse drag into horizontal intent. | Pointer delta / screen position | event OnDrag(float normalizedX) | PlayerMotor | Disable during choice/end screens | One input path; no joystick/inertia. |  | Reset contract | RunController creates RunState and calls IResettable.ResetRun | Makes restart testable and centralized | Proposed | Developer | G1 | One component retains stale state | Automated reset checklist + 10-restart soak
Player | PlayerMotor | MonoBehaviour | Moves player horizontally inside playable bounds. | Base speed + movement modifiers | SetInput(), ApplyMovementModifier() | InputReader, RunState | Reset position and cached input | Auto-forward movement remains stage-driven. |  | Obstacle architecture | Shared ObstacleBase + composition, not inheritance tree | Two obstacles do not justify abstraction cost | Proposed | Claude Code | G1 | Duplicated collision logic | Extract only collision/damage behavior
Player | PlayerHealth | MonoBehaviour | Applies damage, invulnerability and death signal. | Current/max health, invulnerability timer | ApplyDamage(int), event HealthChanged, event Died | ObstacleBase, RunController | Restore health and timer | Start health 3; i-frames 0.8–1.0 s. |  | Content architecture | Fixed StageDefinition catalog | Matches locked six-stage scope | Proposed | Developer | G2 | Design requires runtime variation | Use parameters, not procedural generation
Obstacles | ObstacleBase | MonoBehaviour / prefab base | Common collision, one-hit-per-valid-contact and reset contract. | Damage value, active state | OnPlayerContact(), ResetObstacle() | PlayerHealth | Reset on stage/restart | No deep inheritance; shared component + config. |  | Modifier application | Central ModifierStack with hard caps | Avoids impossible cost combinations | Proposed | Claude Code | G2 | Scattered multipliers create unfair states | Route every effect through CostApplier
Obstacles | SpikeWall | Prefab component | Readable configurable safe corridor. | Gap position/width | Configure(SpikeWallConfig) | ObstacleBase, StageDefinition | Reinitialize per stage | MVP obstacle 1. |  | UI architecture | Passive presenters only | Keeps game rules out of HUD/cards | Proposed | Developer | G3 | UI directly mutates state | Expose commands on RunController/ChoiceGate
Obstacles | MovingBlade | Prefab component | Horizontal blade movement with speed and phase. | Amplitude, speed, phase | Configure(BladeConfig) | ObstacleBase, StageDefinition | Reset phase on restart | MVP obstacle 2. |  | Performance | No pooling unless profiling proves need | Six short fixed stages and two obstacle types | Proposed | Developer | G4 | Instantiation hitch on device | Pre-instantiate six chunks disabled
Content | StageDefinition | ScriptableObject | Static stage chunk config and prefab reference. | Stage ID, prefab, duration, obstacle configs, choice flag | Immutable config fields | StageDirector | Asset lifetime | Six fixed entries only; no procedural generation.
Flow | StageDirector | MonoBehaviour | Loads/activates fixed stage chunks, advances once, prevents soft locks. | StageCatalog, current chunk | StartStage(index), CompleteCurrentStage(), event StageChanged | RunController, StageDefinition | Unload/deactivate chunk on transition | Single gameplay scene; stage prefabs as children.
Choice | CostData | ScriptableObject | Data for one offer: icon, copy, benefit, cost/risk type and value. | Immutable offer content | CostType, Value, Benefit ID | ChoiceGate, CostApplier, DecisionCard | Asset lifetime | Stable public API; no scene logic.
Choice | ChoiceGate | MonoBehaviour | Presents two physical altars; commits exactly one selection once. | Two CostData offers, selection lock | event CostChosen(CostData) | RunController, CostApplier | Clear selection lock each stage | No confirmation button.
Choice | CostApplier | Plain service / component | Applies bounded permanent run modifiers. | RunState modifier stack | Apply(CostData), ValidateCaps() | CostData, RunState | State removed by new RunState | Blood / Light / Sight / Body only.
Choice | ModifierStack | Plain class | Centralizes cumulative modifiers and clamps fairness limits. | Movement, body scale, sight, max health/light impacts | GetEffectiveStats(), AddModifier() | CostApplier, PlayerMotor, presentation | New per run | One source of truth; no scattered multipliers.
Resource | RelicLight | MonoBehaviour presenter/service | Tracks 0–100 light separately from health and raises changes. | RunState.light | ChangeLight(), event LightChanged | CostApplier, HUD, EndingResolver | Reset to 100 | May reach 0; clamp 0–100.
Ending | EndingResolver | Plain service | Maps final light thresholds to at least two outcomes. | EndingDefinition list, RunState.light | Resolve(light) | RunController, OutcomeScreen | Stateless | Target 3 endings; minimum 2 after G3.
UI | HUDPresenter | MonoBehaviour | Displays health, stage and light; contains no game logic. | Events from health/light/stage | Bind()/Unbind() | PlayerHealth, RelicLight, StageDirector | Refresh on run start | Safe-area aware.
UI | Screen Presenters | MonoBehaviours | Start hint, decision cards and outcome/Retry. | View models only | Show()/Hide()/SetData() | RunController, ChoiceGate, EndingResolver | Clear transient UI on restart | Short icon-heavy English copy.
Feedback | FeedbackController | MonoBehaviour | Essential SFX, impact flash and stage transition feedback. | Audio clips / simple VFX refs | PlayDamage(), PlayChoice(), PlayTransition() | Gameplay events | Stop/clear on restart | Music optional; shadow must read muted.
Build | BuildConfig | ScriptableObject / project settings | Defines portrait target, safe area and primary platform. | Platform, orientation, reference aspect | Read-only configuration | GameBootstrap, UI | Asset lifetime | Android default; WebGL only if rules require.
DO NOT BUILD
Combat • procedural generation • inventory • dialogue trees • character classes • online features • complex meta-progression • any feature that delays the critical path

## Backlog
ID | Title | Epic | Priority | Gate | Est. h | Dependencies | Status | Owner | Planned Start h | Planned End h | Actual h | % Complete | Dependency State | Blocker | Acceptance Criteria | Implementation Note | Test Result | Changed Files | Last Update | Critical Path
LL-001 | Create portrait project baseline and Pixel Perfect camera | E1 Core Controller | Must | G1 | 1 | None | Ready | Developer | 0 | 1 |  | 0% | Ready |  | Scene runs at 9:16 reference resolution with correct camera framing and no Console errors. | Critical path | Not Run |  |  | Yes
LL-002 | Implement touch and mouse horizontal drag movement | E1 Core Controller | Must | G1 | 2 | LL-001 | Backlog | Developer | 1 | 3 |  | 0% | Waiting on tasks |  | A first-time player can move left and right within 10 seconds using mouse or one finger. | No inertia or joystick | Not Run |  |  | Yes
LL-003 | Implement health, damage and invulnerability | E2 Survival Loop | Must | G1 | 2 | LL-002 | Backlog | Developer | 3 | 5 |  | 0% | Waiting on tasks |  | Obstacle contact removes one health and repeated contact is blocked for 0.8-1.0 seconds. | Start health 3 | Not Run |  |  | Yes
LL-004 | Implement death and fast restart | E2 Survival Loop | Must | G1 | 1.5 | LL-003 | Backlog | Developer | 5 | 6.5 |  | 0% | Waiting on tasks |  | At zero health the run ends and a new run begins within five seconds with all state reset. | Protected core | Not Run |  |  | Yes
LL-005 | Build reusable obstacle base and collision setup | E3 Obstacle Framework | Must | G1 | 1.5 | LL-003 | Backlog | Claude Code | 5 | 6.5 |  | 0% | Waiting on tasks |  | Obstacle prefabs damage the player once per valid contact and reset correctly. | Critical path | Not Run |  |  | Yes
LL-006 | Create spike wall prefab and variations | E3 Obstacle Framework | Must | G1 | 1 | LL-005 | Backlog | Developer | 6.5 | 7.5 |  | 0% | Waiting on tasks |  | Spike wall has a clearly readable safe corridor and configurable gap position and width. | MVP obstacle 1 | Not Run |  |  | Yes
LL-007 | Create moving blade prefab | E3 Obstacle Framework | Must | G1 | 1.5 | LL-005 | Backlog | Claude Code | 6.5 | 8 |  | 0% | Waiting on tasks |  | Blade moves horizontally with configurable speed and phase and remains visually readable. | MVP obstacle 2 | Not Run |  |  | No
LL-008 | Implement stage start, completion and sequence flow | E4 Level Flow | Must | G2 | 2 | LL-004, LL-006 | Backlog | Developer | 8 | 10 |  | 0% | Waiting on tasks |  | A stage starts, progresses automatically, completes once, and transitions without soft lock. | Critical path | Not Run |  |  | Yes
LL-009 | Create CostData ScriptableObject | E5 Choice & Cost | Must | G2 | 1 | LL-008 | Backlog | Claude Code | 10 | 11 |  | 0% | Waiting on tasks |  | An offer stores icon, short copy, benefit, cost or risk type, and value without scene-specific logic. | Stable public API | Not Run |  |  | Yes
LL-010 | Implement physical two-offer ChoiceGate | E5 Choice & Cost | Must | G2 | 2 | LL-008, LL-009 | Backlog | Developer | 11 | 13 |  | 0% | Waiting on tasks |  | Dragging into an altar selects exactly one offer, applies it once, and advances the flow. | No confirmation button | Not Run |  |  | Yes
LL-011 | Implement CostApplier and modifier caps | E5 Choice & Cost | Must | G2 | 2.5 | LL-009, LL-010 | Backlog | Claude Code | 13 | 15.5 |  | 0% | Waiting on tasks |  | At least one permanent cost visibly affects the next stage and all modifiers respect documented limits. | Blood, Light, Sight, Body | Not Run |  |  | Yes
LL-012 | Implement relic light resource | E6 Relic & Endings | Must | G2 | 1 | LL-011 | Backlog | Developer | 15 | 16 |  | 0% | Waiting on tasks |  | Light starts at 100%, updates through events, may reach 0%, and resets on restart. | Separate from health | Not Run |  |  | Yes
LL-013 | Implement ending resolver and outcome screen | E6 Relic & Endings | Must | G3 | 2 | LL-012 | Backlog | Developer | 16 | 18 |  | 0% | Waiting on tasks |  | At least two endings trigger correctly from remaining-light thresholds and show Retry. | Target 3, minimum 2 | Not Run |  |  | Yes
LL-014 | Assemble six fixed stage chunks | E4 Level Flow | Must | G3 | 4 | LL-007, LL-008, LL-011 | Backlog | Claude Code | 16 | 20 |  | 0% | Waiting on tasks |  | The game completes from opening through six stages to an ending in under five minutes. | Use placeholders first | Not Run |  |  | Yes
LL-015 | Create start screen and micro-tutorial | E7 UX/UI | Must | G3 | 1 | LL-002 | Backlog | Developer | 18 | 19 |  | 0% | Waiting on tasks |  | Tap starts the run and the drag hint disappears after first movement. | Short English copy | Not Run |  |  | Yes
LL-016 | Create HUD for health, stage and light | E7 UX/UI | Must | G3 | 1.5 | LL-003, LL-012 | Backlog | Developer | 19 | 20.5 |  | 0% | Waiting on tasks |  | HUD reflects health, current stage and light without containing game logic. | Safe area required | Not Run |  |  | Yes
LL-017 | Create concise decision cards | E7 UX/UI | Must | G3 | 1.5 | LL-009, LL-010 | Backlog | Claude Code | 20 | 21.5 |  | 0% | Waiting on tasks |  | Each card shows an icon, one benefit line, and Cost or Risk copy within roughly 8-12 words. | Readability gate | Not Run |  |  | Yes
LL-018 | Run first real-device input test | E9 QA & Submission | Must | G4 | 1 | LL-002, LL-004 | Backlog | QA / Developer | 28 | 29 |  | 0% | Waiting on tasks |  | Input, safe area and frame rate are acceptable on at least one Android device. | Mandatory early test | Not Run |  |  | Yes
LL-019 | Pass min-speed and max-body fairness matrix | E9 QA & Submission | Must | G5 | 1.5 | LL-011, LL-014 | Backlog | QA / Claude Code | 29 | 30.5 |  | 0% | Waiting on tasks |  | Every stage is passable at minimum allowed movement speed and maximum character size. | Block release if failed | Not Run |  |  | Yes
LL-020 | Replace critical placeholders with minimum pixel-art set | E8 Art/Audio Polish | Should | G5 | 4 | G3 passed | Backlog | Art | 28 | 32 |  | 0% | Waiting on gate |  | Traveller, light, two obstacles, altar and minimum ending visuals are readable and integrated. | Must not block critical path | Not Run |  |  | No
LL-021 | Add essential SFX and impact feedback | E8 Art/Audio Polish | Should | G5 | 1.5 | G3 passed | Backlog | Audio / Developer | 32 | 33.5 |  | 0% | Waiting on gate |  | Damage, cost selection and stage transition have clear feedback; shadow remains readable muted. | Music optional | Not Run |  |  | No
LL-022 | Run external playtest and decision review | E9 QA & Submission | Must | G5 | 1.5 | G3 passed | Backlog | PM / QA | 33.5 | 35 |  | 0% | Waiting on gate |  | Record control comprehension, cost clarity, fairness, run time and retry intent; convert findings into prioritized fixes. | 5-10 rapid tests | Not Run |  |  | Yes
LL-023 | Feature freeze and blocker-only pass | E9 QA & Submission | Must | G6 | 4 | G5 passed | Backlog | Developer + QA | 38 | 42 |  | 0% | Waiting on gate |  | Only blocker, build and readability fixes are accepted; zero blocker bugs remain. | Begins with 10 hours remaining | Not Run |  |  | Yes
LL-024 | Create final build and submission assets | E9 QA & Submission | Must | G6 | 3 | LL-023 | Backlog | Developer + PM | 42 | 45 |  | 0% | Waiting on tasks |  | Final build, controls, description, screenshots and submission page are complete and smoke-tested. | Primary Android unless rules require WebGL | Not Run |  |  | Yes

## Milestones
Gate | Name | Target Hour | Pass Condition | PM Rule | Tasks | Planned h | Done h | Progress | Gate Status | Owner | Evidence / Notes
G1 | Core playable | 8 | Character moves, takes damage, dies and restarts. | Proceed only when restart is stable. | LL-001 to LL-007 | 10.5 | 0 | 0% | Not Started | PM / Lead
G2 | Theme playable | 16 | Two decisions exist and one permanent cost is felt in the next stage. | Vertical slice must validate the theme. | LL-008 to LL-012 | 8.5 | 0 | 0% | Not Started | PM / Lead
G3 | End-to-end | 28 | Six stages complete from opening to ending. | Cut optional systems if this gate slips. | LL-013 to LL-017 | 10 | 0 | 0% | Not Started | PM / Lead
G4 | Mobile usable | 32 | Input, safe area and performance pass on a real device. | Blocking mobile gate. | LL-018 | 1 | 0 | 0% | Not Started | PM / Lead
G5 | Content complete | 38 | Two obstacles, four costs/risks, two endings and essential UI are complete. | Start feature freeze after this gate. | LL-019 to LL-022 | 8.5 | 0 | 0% | Not Started | PM / Lead
G6 | Submission ready | 48 | No blockers; build, description, screenshots and controls are ready. | Ship stable over ambitious. | LL-023 to LL-024 | 7 | 0 | 0% | Not Started | PM / Lead

## 48h Plan
48-Hour Delivery Plan & Proposed Parallel Schedule
Start | End | Goal | Tasks | Allowed Work | Cut Trigger | Gate
0 | 8 | Core playable | LL-001 to LL-007 | Control, survival, two obstacles | No polish before restart is stable | G1
8 | 16 | Theme vertical slice | LL-008 to LL-012 | Stage flow, choice, first costs, light | Use placeholder UI and art | G2
16 | 28 | End-to-end run | LL-013 to LL-017 | Six stages, ending, essential UX | Cut third obstacle and variation | G3
28 | 38 | Mobile, content and playtest | LL-018 to LL-022 | Device fixes, fairness, minimum art/audio | Cut music layers and extra endings | G4 / G5
38 | 48 | Feature freeze | LL-023 to LL-024 | Blocker, build and readability fixes only | No new systems | G6
Gantt — 2-hour buckets
ID | Task | Owner | Start h | End h | Duration | Gate | 0 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48
LL-001 | Create portrait project baseline and Pixel Perfect camera | Developer | 0 | 1 | 1 | G1
LL-002 | Implement touch and mouse horizontal drag movement | Developer | 1 | 3 | 2 | G1
LL-003 | Implement health, damage and invulnerability | Developer | 3 | 5 | 2 | G1
LL-004 | Implement death and fast restart | Developer | 5 | 6.5 | 1.5 | G1
LL-005 | Build reusable obstacle base and collision setup | Claude Code | 5 | 6.5 | 1.5 | G1
LL-006 | Create spike wall prefab and variations | Developer | 6.5 | 7.5 | 1 | G1
LL-007 | Create moving blade prefab | Claude Code | 6.5 | 8 | 1.5 | G1
LL-008 | Implement stage start, completion and sequence flow | Developer | 8 | 10 | 2 | G2
LL-009 | Create CostData ScriptableObject | Claude Code | 10 | 11 | 1 | G2
LL-010 | Implement physical two-offer ChoiceGate | Developer | 11 | 13 | 2 | G2
LL-011 | Implement CostApplier and modifier caps | Claude Code | 13 | 15.5 | 2.5 | G2
LL-012 | Implement relic light resource | Developer | 15 | 16 | 1 | G2
LL-013 | Implement ending resolver and outcome screen | Developer | 16 | 18 | 2 | G3
LL-014 | Assemble six fixed stage chunks | Claude Code | 16 | 20 | 4 | G3
LL-015 | Create start screen and micro-tutorial | Developer | 18 | 19 | 1 | G3
LL-016 | Create HUD for health, stage and light | Developer | 19 | 20.5 | 1.5 | G3
LL-017 | Create concise decision cards | Claude Code | 20 | 21.5 | 1.5 | G3
LL-018 | Run first real-device input test | QA / Developer | 28 | 29 | 1 | G4
LL-019 | Pass min-speed and max-body fairness matrix | QA / Claude Code | 29 | 30.5 | 1.5 | G5
LL-020 | Replace critical placeholders with minimum pixel-art set | Art | 28 | 32 | 4 | G5
LL-021 | Add essential SFX and impact feedback | Audio / Developer | 32 | 33.5 | 1.5 | G5
LL-022 | Run external playtest and decision review | PM / QA | 33.5 | 35 | 1.5 | G5
LL-023 | Feature freeze and blocker-only pass | Developer + QA | 38 | 42 | 4 | G6
LL-024 | Create final build and submission assets | Developer + PM | 42 | 45 | 3 | G6

## QA Matrix
Test ID | Type | System | Scenario / Requirement | Expected Result | Gate | Device / Mode | Severity | Owner | Status | Evidence / Notes
T-001 | Task Acceptance | E1 Core Controller | Create portrait project baseline and Pixel Perfect camera | Scene runs at 9:16 reference resolution with correct camera framing and no Console errors. | G1 | Unity Play Mode | Blocker | Developer | Not Run
T-002 | Task Acceptance | E1 Core Controller | Implement touch and mouse horizontal drag movement | A first-time player can move left and right within 10 seconds using mouse or one finger. | G1 | Unity Play Mode | Blocker | Developer | Not Run
T-003 | Task Acceptance | E2 Survival Loop | Implement health, damage and invulnerability | Obstacle contact removes one health and repeated contact is blocked for 0.8-1.0 seconds. | G1 | Unity Play Mode | Blocker | Developer | Not Run
T-004 | Task Acceptance | E2 Survival Loop | Implement death and fast restart | At zero health the run ends and a new run begins within five seconds with all state reset. | G1 | Unity Play Mode | Blocker | Developer | Not Run
T-005 | Task Acceptance | E3 Obstacle Framework | Build reusable obstacle base and collision setup | Obstacle prefabs damage the player once per valid contact and reset correctly. | G1 | Unity Play Mode | Blocker | Claude Code | Not Run
T-006 | Task Acceptance | E3 Obstacle Framework | Create spike wall prefab and variations | Spike wall has a clearly readable safe corridor and configurable gap position and width. | G1 | Unity Play Mode | Blocker | Developer | Not Run
T-007 | Task Acceptance | E3 Obstacle Framework | Create moving blade prefab | Blade moves horizontally with configurable speed and phase and remains visually readable. | G1 | Unity Play Mode | Blocker | Claude Code | Not Run
T-008 | Task Acceptance | E4 Level Flow | Implement stage start, completion and sequence flow | A stage starts, progresses automatically, completes once, and transitions without soft lock. | G2 | Unity Play Mode | Blocker | Developer | Not Run
T-009 | Task Acceptance | E5 Choice & Cost | Create CostData ScriptableObject | An offer stores icon, short copy, benefit, cost or risk type, and value without scene-specific logic. | G2 | Unity Play Mode | Blocker | Claude Code | Not Run
T-010 | Task Acceptance | E5 Choice & Cost | Implement physical two-offer ChoiceGate | Dragging into an altar selects exactly one offer, applies it once, and advances the flow. | G2 | Unity Play Mode | Blocker | Developer | Not Run
T-011 | Task Acceptance | E5 Choice & Cost | Implement CostApplier and modifier caps | At least one permanent cost visibly affects the next stage and all modifiers respect documented limits. | G2 | Unity Play Mode | Blocker | Claude Code | Not Run
T-012 | Task Acceptance | E6 Relic & Endings | Implement relic light resource | Light starts at 100%, updates through events, may reach 0%, and resets on restart. | G2 | Unity Play Mode | Blocker | Developer | Not Run
T-013 | Task Acceptance | E6 Relic & Endings | Implement ending resolver and outcome screen | At least two endings trigger correctly from remaining-light thresholds and show Retry. | G3 | Unity Play Mode | Blocker | Developer | Not Run
T-014 | Task Acceptance | E4 Level Flow | Assemble six fixed stage chunks | The game completes from opening through six stages to an ending in under five minutes. | G3 | Unity Play Mode | Blocker | Claude Code | Not Run
T-015 | Task Acceptance | E7 UX/UI | Create start screen and micro-tutorial | Tap starts the run and the drag hint disappears after first movement. | G3 | Unity Play Mode | Blocker | Developer | Not Run
T-016 | Task Acceptance | E7 UX/UI | Create HUD for health, stage and light | HUD reflects health, current stage and light without containing game logic. | G3 | Unity Play Mode | Blocker | Developer | Not Run
T-017 | Task Acceptance | E7 UX/UI | Create concise decision cards | Each card shows an icon, one benefit line, and Cost or Risk copy within roughly 8-12 words. | G3 | Unity Play Mode | Blocker | Claude Code | Not Run
T-018 | Task Acceptance | E9 QA & Submission | Run first real-device input test | Input, safe area and frame rate are acceptable on at least one Android device. | G4 | Android device | Blocker | QA / Developer | Not Run
T-019 | Task Acceptance | E9 QA & Submission | Pass min-speed and max-body fairness matrix | Every stage is passable at minimum allowed movement speed and maximum character size. | G5 | Unity Play Mode | Blocker | QA / Claude Code | Not Run
T-020 | Task Acceptance | E8 Art/Audio Polish | Replace critical placeholders with minimum pixel-art set | Traveller, light, two obstacles, altar and minimum ending visuals are readable and integrated. | G5 | Unity Play Mode | Major | Art | Not Run
T-021 | Task Acceptance | E8 Art/Audio Polish | Add essential SFX and impact feedback | Damage, cost selection and stage transition have clear feedback; shadow remains readable muted. | G5 | Unity Play Mode | Major | Audio / Developer | Not Run
T-022 | Task Acceptance | E9 QA & Submission | Run external playtest and decision review | Record control comprehension, cost clarity, fairness, run time and retry intent; convert findings into prioritized fixes. | G5 | Unity Play Mode | Blocker | PM / QA | Not Run
T-023 | Task Acceptance | E9 QA & Submission | Feature freeze and blocker-only pass | Only blocker, build and readability fixes are accepted; zero blocker bugs remain. | G6 | Unity Play Mode | Blocker | Developer + QA | Not Run
T-024 | Task Acceptance | E9 QA & Submission | Create final build and submission assets | Final build, controls, description, screenshots and submission page are complete and smoke-tested. | G6 | Unity Play Mode | Blocker | Developer + PM | Not Run
T-025 | Cross-system | Restart | Complete 10 death/retry cycles after different costs | No stale modifiers, duplicate events, disabled input or retained stage objects | G3 | Play Mode | Blocker | Developer / QA | Not Run
T-026 | Cross-system | Choice | Enter both altar colliders rapidly / multi-touch | Exactly one CostData commits and stage advances once | G2 | Play Mode + device | Blocker | QA | Not Run
T-027 | Fairness | Modifiers | Minimum movement speed + maximum body size across six stages | Every corridor and blade timing remains passable | G5 | Play Mode + device | Blocker | QA / Claude Code | Not Run
T-028 | Boundary | Relic / Ending | Finish with relic light exactly 0 | Valid ending resolves; no negative value or soft lock | G3 | Play Mode | Blocker | Developer | Not Run
T-029 | Boundary | Ending | Test values one unit below/at/above each ending threshold | Every value maps to exactly one outcome | G3 | Play Mode | Major | QA | Not Run
T-030 | Performance | Full Run | Three complete runs with different choices | Each run completes in 3–5 minutes with stable frame pacing | G5 | Android device | Blocker | QA / PM | Not Run
T-031 | Mobile UX | Safe Area | Test representative 9:16 devices with notch/navigation insets | HUD and cards remain visible and tappable | G4 | Android device | Blocker | Developer / QA | Not Run
T-032 | Readability | Visuals | Play muted and with low screen brightness | Shadow, damage, safe corridors and choices remain readable | G5 | Android device | Major | Art / QA | Not Run
T-033 | Stability | Console | Run full game and restart repeatedly | No new errors; warnings are reviewed and accepted | G6 | Development build | Blocker | Developer | Not Run
T-034 | Submission | Build | Fresh install final package and follow listed controls | Launch, play, retry and exit work; screenshots/description match build | G6 | Target platform | Blocker | PM / QA | Not Run

## Risks & Decisions
Decisions, Risks and Scope Guardrails
Decision ID | Area | Decision | Status | Source | Owner | Review Gate | Notes
D-01 | Scope | No feature is added unless another feature is removed. | Accepted | DECISIONS.md | PM | All | Locked scope rule
D-02 | Build | Android by default; switch to WebGL only if jam rules require it. | Pending | DECISIONS.md | PM | G1 | Confirm jam submission rules immediately
D-03 | Language | Use icon-heavy short English copy. | Accepted | DECISIONS.md | Design | G3 | Protect mobile readability
D-04 | Endings | Three target, two minimum; decide after G3. | Pending | DECISIONS.md | PM / Design | G3 | Cut third ending if gate slips
D-05 | Core Loop | Auto-run, horizontal drag, avoidance, end-stage choice, permanent sacrifice. | Locked | DECISIONS.md | Lead | All | Protected pillar
D-06 | Resources | Health and relic light are separate resources. | Locked | DECISIONS.md | Lead | G2 | Do not merge into one meter
D-07 | Run Structure | Six short fixed stages; total run 3–5 minutes. | Locked | DECISIONS.md | Lead | G3 | No procedural stage generation
D-08 | Freeze | Feature freeze at Hour 38; blockers/build/readability only. | Locked | DECISIONS.md | PM | G5 | No new systems
D-09 | Architecture | One scene + stage prefabs + immutable ScriptableObject config + mutable RunState. | Proposed | Architecture sheet | Developer | G1/G2 | Accept before implementation spreads
D-10 | Modifier Caps | All Blood/Light/Sight/Body effects route through one capped ModifierStack. | Proposed | Architecture sheet | Developer | G2 | Prevents impossible combinations
Risk ID | Risk | Category | Likelihood | Impact | Score | Trigger | Mitigation / Response | Owner | Status | Linked Gate
R-01 | Scope growth | Product | 3 | 3 | 9 | Any new feature request | Move to Parking Lot unless it explicitly replaces existing scope. | PM | Open | All
R-02 | Mobile input feel | Technical | 2 | 3 | 6 | Drag feels laggy or imprecise on device | Run early real-device test; tune smoothing and bounds before polish. | Developer | Open | G4
R-03 | Impossible cost combinations | Design / Technical | 2 | 3 | 6 | Any stage fails min-speed/max-body matrix | Central caps; test every stage at worst-case modifier combination. | Developer / QA | Open | G5
R-04 | Insufficient schedule buffer | Delivery | 3 | 3 | 9 | Gate slips by >1 hour | Cut Should tasks and third ending; preserve QA and build time. | PM | Open | All
R-05 | Restart state leakage | Technical | 2 | 3 | 6 | Second run differs due to stale events/modifiers | Fresh RunState; explicit reset contract; 10-restart soak test. | Developer | Open | G1/G3
R-06 | Stage transition soft lock | Technical | 2 | 3 | 6 | Completion or choice fires twice / never fires | Single RunController phase authority; idempotent completion guards. | Developer | Open | G2/G3
R-07 | Late Android build failure | Build | 2 | 3 | 6 | No installable device build by Hour 28 | Create first development build at G3 and smoke test immediately. | Developer | Open | G4/G6
R-08 | Mobile readability failure | UX | 2 | 3 | 6 | Choices or hazards unclear at device size | Safe-area UI; icon-first cards; muted/low-brightness readability test. | Design / QA | Open | G3/G5
Explicitly Out of Scope | Reason | Disposition
Combat | Not required for protected MVP | Parking Lot / reject
Procedural generation | Not required for protected MVP | Parking Lot / reject
Inventory systems | Not required for protected MVP | Parking Lot / reject
Dialogue trees | Not required for protected MVP | Parking Lot / reject
Multiple character classes | Not required for protected MVP | Parking Lot / reject
Online features | Not required for protected MVP | Parking Lot / reject
Complex meta-progression | Not required for protected MVP | Parking Lot / reject
Any feature that delays the critical path | Not required for protected MVP | Parking Lot / reject

## Content & Tuning
Content Blueprint & Tuning Guardrails
Source-backed values are marked Locked/Accepted. Proposed tuning values are starting points and must be confirmed through the G4/G5 device and fairness tests.
Parameter | Value | Status | Source | Validation
Reference aspect | 9:16 portrait | Accepted | LL-001 / product pillar | Real-device safe-area pass
Start health | 3 | Accepted | LL-003 | Damage and restart tests
Invulnerability | 0.8–1.0 s | Accepted | LL-003 | Repeated-contact test
Relic light start | 100 | Accepted | LL-012 | Clamp and reset test
Stage count | 6 | Locked | DECISIONS.md | End-to-end gate
Run duration | 3–5 min | Locked | DECISIONS.md | Three full-run measurements
Offers per gate | 2 | Accepted | LL-010 | Single-selection test
Ending count | 2 minimum / 3 target | Pending | DECISIONS.md | Decision after G3
Movement speed floor | 70% of baseline | Proposed | Senior-dev planning | Fairness matrix
Body scale ceiling | 125% of baseline | Proposed | Senior-dev planning | Fairness matrix
Max-health floor | 1 | Proposed | Senior-dev planning | Cost-combination test
Sight visibility floor | 65% useful playfield | Proposed | Senior-dev planning | Mobile readability test
Stage | Purpose | Primary Hazard | Secondary Pressure | Choice After Stage? | Target Duration | Tuning Focus | Exit Criteria
1 | Teach drag and safe corridor | Spike wall | None / generous gap | Yes | 25–35 s | Control comprehension | Player reaches gate without text-heavy tutorial
2 | Teach blade timing | Moving blade | Wide corridor | Yes | 25–35 s | Readable timing | Player understands moving hazard
3 | Combine learned hazards | Spike + blade | First permanent cost active | Yes | 30–40 s | Cost is visibly felt | No unfair overlap
4 | Raise tempo | Alternating corridors | Faster blade phase | Yes | 30–40 s | Speed/body cap safety | Passable at worst movement modifier
5 | Decision consequence peak | Mixed fixed pattern | Reduced sight or light pressure | Yes | 35–45 s | Readability under costs | Fairness matrix passes
6 | Final gauntlet and resolve | Best two patterns | No new mechanics | No — resolve ending | 35–50 s | Climax without novelty | Ending triggers and Retry is shown
Cost Type | Runtime Variable | Example Cost | Hard Cap | Example Benefit | Implementation | Player Feedback | QA Boundary | Status | Owner | Notes
Blood | Max/current health | -1 max health | Minimum 1 | Wider safe corridor in next stage | ModifierStack + PlayerHealth refresh | Heart cracks / red flash | Apply repeatedly to floor | Proposed | Design / Dev | Keep separate from relic light
Light | Relic light | -15 to -25 light | Clamp 0–100 | Remove one hazard or slow stage pressure | RelicLight.ChangeLight | Relic dims; HUD pulse | 0, threshold−1, threshold, threshold+1 | Proposed | Design / Dev | Light can reach 0
Sight | Visibility mask | Reduce useful view area | Minimum 65% useful playfield | Reveal safe lane earlier / simplify pattern | SightPresenter reads ModifierStack | Vignette closes gradually | Lowest sight on smallest device | Proposed | Design / Art | Never hide critical collision cues
Body | Move speed or body scale | -10% speed or +10% size | Speed ≥70%; scale ≤125% | Slower obstacle / wider gap | PlayerMotor + visual scale from one modifier | Silhouette grows / motion changes | Min speed + max body on every stage | Proposed | Design / Dev | Avoid applying both speed and size in one offer

## Read Me
How to Use This Planning Workbook
Area | Instructions |  |  | Planning Assumptions
Dashboard | Update Elapsed jam hours. KPIs and gate health recalculate from Backlog and Milestones. |  |  | • Unity 2D is inferred from Pixel Perfect camera and Unity Play Mode requirements. • The schedule uses parallel Developer / Claude Code / Art / QA lanes because G1 contains 10.5 estimated hours but targets Hour 8. • Technical architecture, stage blueprint and modifier caps are senior-developer proposals; confirm them at the stated review gates. • No new gameplay system should be introduced after Hour 38.
Backlog | Change Status, Owner, Actual h, Blocker, Test Result, Changed Files and Last Update. Do not start work unless Dependency State is Ready.
Architecture | Accept or adjust proposed architecture decisions before G1/G2. Keep the system intentionally small.
Milestones | A gate passes only when all linked tasks are Done and the pass condition has evidence.
48h Plan | Use the proposed parallel lanes as a starting point. Preserve Hour 38 feature freeze and final build buffer.
QA Matrix | Every task has a matching acceptance test plus cross-system, mobile, fairness and submission tests.
Risks & Decisions | Resolve pending build target immediately and ending count after G3. Review high risk scores daily.
Content & Tuning | Proposed modifier caps are hypotheses, not facts; confirm through device/fairness testing.
Status Workflow | Backlog → Ready → In Progress → Review/Test → Done. A task is not Done until tested.
Scope Rule | No feature is added unless another feature is removed.
Source File | Purpose | Authority | Notes
DECISIONS.md | Locked product decisions, risks and out-of-scope list | High | Read first
ROADMAP.md | 48-hour phases, milestone gates and critical path | High | Gate timing source
TASKS.md | Authoritative implementation queue and acceptance criteria | Highest | Status source of truth
Last_Light_Project_Plan.pdf | Human-readable consolidated production plan | Reference | Visually verified: 7 pages
README.md | Package usage instructions | Reference | Claude Code sequencing instructions